## Gantt Chart
GANTT CHART - Kiosk
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15
[6 empty] | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su
BASIC FEATURES
| Make the Database | 2/30/2019 | 2019-03-14 | 14 | Adam | bar: WEEK 8 F to WEEK 10 Su; WEEK 12 M to WEEK 12 F
| Python Database Connection | 2/30/2019 | 2019-03-14 | 14 | Jeff | bar: WEEK 8 M to WEEK 8 T; WEEK 8 F to WEEK 10 Su; WEEK 12 M to WEEK 12 F
| Interface | 2/30/2019 | 2019-03-14 | 14 | Shanuak | bar: WEEK 8 M to WEEK 8 T; WEEK 8 F to WEEK 10 Su; WEEK 12 M to WEEK 12 F
MEDIUM
| Confirmation Email | 2019-03-14 | 2019-03-21 | 7 | Adam | bar: WEEK 8 F to WEEK 8 Su; WEEK 10 M to WEEK 11 F; WEEK 12 M to WEEK 12 F
|  |  |  | 7 | Shanuak | bar: WEEK 8 F to WEEK 8 Su; WEEK 10 M to WEEK 11 F; WEEK 12 M to WEEK 12 F
|  |  |  | 7 | Jeff | bar: WEEK 8 F to WEEK 8 Su; WEEK 10 M to WEEK 11 F; WEEK 12 M to WEEK 12 F
ADVANCED FEATURES
| Current Location | 2019-03-21 | 2019-03-28 | 7 | Adam | bar: WEEK 8 F to WEEK 8 Su; WEEK 10 M to WEEK 10 Su; WEEK 11 F to WEEK 12 F
|  |  |  | 7 | Jeff | bar: WEEK 8 F to WEEK 8 Su; WEEK 10 M to WEEK 10 Su; WEEK 11 F to WEEK 12 F
|  |  |  | 7 | Shanuak | bar: WEEK 8 F to WEEK 8 Su; WEEK 10 M to WEEK 10 Su; WEEK 11 F to WEEK 12 F
| Master Ticket | 2019-03-21 | 2019-03-28 |  | Jeff | bar: WEEK 8 F to WEEK 8 Su; WEEK 10 M to WEEK 10 Su; WEEK 12 M to WEEK 12 F
|  |  |  | 0 | Adam | bar: WEEK 8 F to WEEK 8 Su; WEEK 10 M to WEEK 10 Su; WEEK 12 M to WEEK 12 F
| User interface | 1930-03-01 | 2019-03-28 |  | Shawn | bar: WEEK 8 F to WEEK 12 F
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])